## Slide 1
Program Charter
MuleSoft Pilot
Version History | Date | Revised by | Change Summary | Approved By
V1.0 | 10.02.2022 | Kavitha Golagani | Draft | 

## Slide 2: Business Process Framework To achieve Business Process Excellence we need to effectively integrate these elements
Results | What business results are we targeting, over what period?
Strategy | What strategies do we have to achieve these results? What changes are needed to our key business processes? Expressed in metrics where possible.
Governance | How is the process governed to ensure these required outcomes? Who has what decision rights? What is Global, Regional or Local.
Metrics | What are the KPI’s that express the end-to-end performance? Sub process performance? Who are accountable for these? Do we have good benchmarks?
Process | What is the optimum process design to deliver the required business performance? Do we have industry best practices?
People | What skills, organization, motivation and incentive are required to execute the process and deliver the performance?
Technology | What are the required technology enablers? What is best practice to leverage that technology?
Design
Implement

## Slide 3: 1. Project Purpose/Expected Results
As part of MDLZ Global Digitalization Strategy , MDLZ identified the need for API Led Integration . Mule Soft is the chosen Technology to support the endeavor. Purpose of this project is to implement a Mule platform and build Integration for ANZ & Canada – ACTPM pilot.
With implementation of Sales Force in October 2021, there is requirement to implement MuleSoft for integration to over come some of the pain points of the past implementations of Retail Execution projects
Replacing Middleware systems that are approaching end of life with Mule Soft and harmonize the landscape
Build an API based Application Network that has better availability , reusability and security following Mule Soft Framework and guidelines.
Reduce dependency on core SAP Systems - Releases to make changes.
Project Purpose
Expected Results
Architect and deliver Composable API Framework . Deploy and run Mule Soft platform , integrated with Multi cloud landscape.
Deliver ANZ (~ 40) & Canada Interfaces to support Business Go live using API Design approach that is accustomed to reuse.
API prototyping using RAML to showcase iterative API specification driven design.
Ensure development & test cycles governed by collaboration tools and code repositories.
Build Exception and Error Handling Framework .
Reduce the over all time to market and cost for future Market deployment

## Slide 4: 2. Project Strategy/Implementation – Pete / David / Kavitha
Project Strategy -
RUN from the start

## Slide 5: 3. Project Scope
Anypoint Cloud Hub platform Setup and configuration
Discovery & Blue printing sessions
Setting up VPN Connection
Define and build the interfaces in scope
Exception Handling
Configuring governing tools to support design /build / Testing and documentation
Any functional processes that are not interfaced are out of scope
In Scope
Out of Scope

## Slide 6: 4. Governance/RACI Matrix – David
Project Sponsor –
SFDC Steering Committee will be the governing body of the Program.
MDLZ Project Team & 3rd Party Vendors will be the planning & execution arm of the project and mainly responsible for implementing the Project plan within defined time, scope & cost.
Governance
Activity/ Work Stream | WS Lead | R | A | C | I
Key | 
Responsible | Owns the problem/Project
Accountable | Who must sign off/Approve on work before it is effective
Consulted | Actively consulted during decision making and has Information and/or capability necessary to complete the work
Informed | Must be notified of Results, but need Not be consulted
RACI Matrix

## Slide 7: 6. Team Structure & Responsibilities – Pete
Team | Name | Role | Responsibility
MDLZ | Thiago | Project Sponsor | Escalation contact, main/final decision maker
MDLZ | Pete Ford | Project Manager | Handling change Management, day to day Project management , aligning with Release Management other stake holders of the larger SFDC program
MDLZ | Kavitha Golagani | Integration Lead | 
MDLZ | David Mickan | MDLZ Enterprise Governance | Project and Platform Governance
MDLZ | Pedro | Project Technical Lead | SME , Design governance , and liaison between Mule Soft Architect and Project development team
Mule Soft |  | MuleSoft Architecture | Build and deliver technical landscape, define framework and document . Available for 8 weeks Only << Align with SoW >>
MDLZ | Villius | Functional Lead | 
Infosys |  | MuleSoft Development Lead | Development Lead , accountable for delivering the interface scope << Align with SoW >>
Infosys |  | MuleSoft Developer | 
Infosys |  | MuleSoft Developer | 
MDLZ |  | SAP Basis Lead | 
MDLZ |  | Automic Lead | 
 |  | Test Management Lead | 
 |  | T2S Lead | 
 |  | Support and Operation Lead | 

## Slide 8: 6. Team Structure & Responsibilities – Kavitha.

## Slide 9
2021
2022
Oct
Nov
Dec
Jan
Feb
Mar
Apr
May
Jun
Jul
04.
11.
18.
25.
01.
08.
15.
22.
29.
06.
13.
20.
27.
03.
10.
17.
24.
31.
07.
14.
21.
28.
07.
14.
21.
28.
04.
11.
18.
25.
02.
09.
16.
23.
30.
06.
13.
20.
27.
04.
11.
18.
25.
App Sprint 4
App Sprint 3
Int Sprint 3
App Sprint 2
Int Sprint 2
App Sprint 1
UAT Execution
Int Sprint 1
UKI & ANZ I&C
Hypercare
SIT (Cycles to be defined)
UAT Prep
Change Management
Environment Readiness
Environment Readiness
2021-12-03
Hypercare
Activity
SIT
Integration
Deploy
BGL: 27th June 2021
ADF Milestones
UAT
Christmas Break
Application
I&C
Scope definition
Build complete
UAT complete
Change Mgmt.
Master data flow complete
Condition Inbound
flow complete
Condition Outbound
Flow complete
Integration Milestones
DEV Env
LQA Env
SQA Env
Build + FUT
Integration Test
UAT-CUT
UAT
System Test
Prod-CUT
Hypercare
ABAP
Integration flows
finalization
D4GV don’t have any fixed plan. They are working in agile mode to deliver Requirements flexible.
Sample Test data
Available for ACTPM
Sample for all Master data
Sample for all Cond. Inbounds
Sample for all Condition Outbounds
Mule Soft
Baseline flow
Settlement, Promo data, Promo P&L, Full P&L, Pricing Condition On/Off-invoice OUT
D4GV
Environment Readiness
Mule Sprint 1
Mule Sprint 2
Mule Sprint 3
Mule Sprint 4
SOW & License Agreements
UAT Execution
BGL: 27th June 2021
ACTPM, Mule , ADF and D4GV – Proposed plan

## Slide 10: 10. Major Risk/issue & Mitigation Plans
Risk/Issue’s Mitigation Plans

## Slide 11: 11. Technology
Technology

## Slide 12: 11. Technology
Future Landscape View

## Slide 13: 7. Change Management Plan & Stakeholder Engagement
Change Management

## Slide 14: 5. Metrics - DEL
Financials
Within project budget
Timelines
On-time delivery
Others
Landscape availability/delivery
# of interfaces migrated/harmonized/redesigned – regional reporting and % of planned
# of defects in T2S – no business disruption (no P2s due to migration)
Post-live # of incidents
Transition to Global Support Model signed-off by support as planned
Metrics/ Project Performance Indicator(s)